## html + css (hidden)
STT | Task | Memo | Is Done
1 | Tạo trang web cơ bản | tạo folder tên comic | Done
2 | Tổ chức cấu trúc folder cho dư án | dùng thẻ h1 tạo title trang, p cho nội dung | Done
3 | dùng thẻ p, h1, h2, ... h6 |  | Done
4

## Hompage
STT | Features | Screen | Component | Sub Component | Task | Assignee | Detail | Pull Request (Link Github) | Estimated Hour (h) | Actual Hour (h) | Start Date | Finish Date | Sprint | Phase | Memo
1 | Home | Home page | Header | navigator top | Create UI | HoangVu | Use "UL tag" to create main navigator top. It have left menu + right menu. |  | 3 | 2 | 2020-10-01 | 2020-10-01 | 1 | 1
2 |  |  |  |  | Create function logic
|  |  |  | navigator top/left | Create UI | HoangVu | Have 3 item inside left menu ( Tro Giup, Tin Tuc, Khuyen Mai), use image PNG to create icon menu left. |  | 2 | 1 | 2020-10-01 | 2020-10-01 | 1 | 1
Create function logic
|  |  |  | navigator top/right | Create UI | HoangVu | Have 3 item inside right menu ( Uu dai va tien ich, Kiem tra don hang, Dang nhap, Dang ky), use image PNG to create icon menu rigt. |  | 2 | 1 | 2020-10-01 | 2020-10-01 | 1 | 1
Create function logic
|  |  |  | Header middle/ Logo Page | Create UI | HoangVu | Use file PNG. Position: on the left page. Size: 117*35 px. |  | 1 | 1 | 2020-10-01 | 2020-10-01 | 1 | 1
Create function logic
3 |  |  |  | Header middle/ Search bar | Create UI | HoangVu | Use "Input tag", it on the middle with icon search, position: middle |  | 1 | 0.5 | 2020-10-01 | 2020-10-01 | 1 | 1
4 |  |  |  |  | Create function logic | HoangVu | input data and press search icon to call searchItem(parameter) | [5 empty] | 1 | 1 |  |  | 1 sprint: thường kéo dài 2 tuần
|  |  |  | Header middle/ Logo search | Create UI | HoangVu | Use file PNG, position: inside search bar |  | 1 | 1 | 2020-10-01 | 2020-10-01 | 1 | 1
|  |  |  | Header middle/ Logo Hotline | Create UI | HoangVu | Use file PNG, position: right middle header bar |  | 1 | 1 | 2020-10-02 | 2020-10-02 | 1 | 1
|  |  |  | Header middle/ Text Hotline | Create UI | HoangVu | Use "P tag" to create. Position: on the right Logo Hotline |  | 1 | 1 | 2020-10-02 | 2020-10-02 | 1 | 1
|  |  |  | Header middle/ Logo Cart | Create UI | HoangVu | Use file PNG, position: right middle header bar |  | 1 | 1 | 2020-10-02 | 2020-10-02 | 1 | 1
|  |  |  | Header middle/ Text Cart | Create UI | HoangVu | Use "P tag" to create. Position: on the right Logo Cart |  | 1 | 1 | 2020-10-02 | 2020-10-02 | 1 | 1 |  |  | 1 sprint: thường kéo dài 2 tuần
|  |  |  | Header bottom/ Icon Item List | Create UI | HoangVu | Use "a, img, span tag" to create. Position: on the left |  | 1 | 1 | 2020-10-04 | 2020-10-04 | 1 | 1
|  |  |  | Header bottom/ Text Item List | Create UI | HoangVu | Use "a, img, span tag" to create. Position: on the right Logo Item List |  | 1 | 1 | 2020-10-04 | 2020-10-04 | 1 | 1
|  |  |  | Header bootom/ menu right | Create UI | HoangVu | Use "a,img,span tag" to create. |  | 1 | 1 | 2020-10-04 | 2020-10-04 | 1 | 1 |  |  | 1 sprint: thường kéo dài 2 tuần
|  |  |  | Header bottom/ Icon Item List | Create UI | HoangVu | Use file PNG, position: left. |  | 1 | 1 | 2020-10-04 | 2020-10-04 | 1 | 1
5 |  |  |  | Header bottom/ Text Item List | Create UI | HoangVu | Use "SPAN tag", position: right. |  | 1 | 1 | 2020-10-04 | 2020-10-04 | 1 | 1 |  |  | 1 phase thường khoản 4 dến 8 sprint
6 |  |  | Body | Main Menu | Create UI | HoangVu | Use "nav, ul tag" create main menu. |  | 3 | 3 | 2020-10-06 | 2020-10-06 | 1 | 1
7 |  |  |  |  | Create function logic | HoangVu
|  |  |  | Sub Menu | Create UI | HoangVu | Use "UL tag" to created. Use display: none. Hidden submenu. |  | 5 | 5 | 2020-10-08 | 2020-10-08 | 1 | 1
[5 empty] | Create function logic | HoangVu | Create link to another page. |  | 1 | 1 | 2020-10-08 | 2020-10-08
8 |  |  |  | Sidebar | Create UI | HoangVu | Use "UL tag" to created sidebar. And use reponsive to show sidebar . |  | 5 | 5 | 2020-10-10 | 2020-10-10 | 1 | 1 |  | Phase | Sprint | Start Date | Finish Date
9 |  |  |  |  | Create function logic |  | Use Jquery Toogle() to hide and show. |  | 1 | 1 | 2020-10-10 | 2020-10-10 | 1 | 1 |  | 1 | 1 | 2020-12-28 | 2020-01-09
10 |  |  |  | SlideShow | Create UI |  | Use Carousel in Bootstrap to created. |  | 1 | 1 | 2020-10-10 | 2020-10-10 | 1 | 1 |  |  | 2 | 2021-01-11 | 2021-01-23
11 |  |  |  |  | Create function logic | [7 empty] | 1 | 1 |  |  | 3 | 2021-01-25 | 2021-02-06
12 |  |  |  | Container Main Image | Create UI | HoangVu | Use "IMG tag" to created. |  | 2 | 2 | 2020-10-12 | 2020-10-12 | 1 | 1 |  |  | 4 | 2021-02-08 | 2021-02-20
13 |  |  |  |  | Create function logic | [7 empty] | 1 | 1
14 |  |  |  | Container Middle Image / Popup | Create UI | HoangVu | Use "div, span tag" to created. When user hover on image it will show. |  | 2 | 2 | 2020-10-12 | 2020-10-12 | 1 | 1
[5 empty] | Create function logic | HoangVu | Create link to ADD TO CART page. |  | 2 | 2 | 2020-10-12 | 2020-10-12
[5 empty] | Create function logic | HoangVu | Create link to BUY NOW page. |  | 2 | 2 | 13/10/2020 | 13/10/2020
15 |  |  |  |  | Create function logic | HoangVu | Create link to ADD TO FAVOURTITE page. |  | 1 | 1 | 13/10/2020 | 13/10/2020 | 1 | 1 |  |  | 1 sprint: thường kéo dài 2 tuần
|  |  | Body | Container Slide Image Books | Create UI | HoangVu | Use Carousel in Bootstrap to created. |  | 1 | 1 | 14/10/2020 | 14/10/2020 | 1 | 1 |  |  | 1 phase thường khoản 4 dến 8 sprint
Create function logic
|  |  |  | Container Main Image | Create UI | HoangVu | Use "IMG tag" to created. |  | 2 | 2 | 14/10/2020 | 14/10/2020 | 1 | 1
Create function logic
|  |  |  | Container Main Image / Book, Comic / Popup | Create UI | HoangVu | Use "DIV, IMG tag" to created popup when move mouse "IMG tag" |  | 3 | 3 | 15/10/2020 | 15/10/2020 | 1 | 1
Create function logic
|  |  |  | Container Main Image / Paint Tool / Popup | Create UI | HoangVu | Use "DIV tag" to created popup when move mouse "IMG tag" and Carousel. |  | 3 | 3 | 15/10/2020 | 15/10/2020 | 1 | 1
Create function logic
|  |  |  | Container Main Image / Technology / Popup | Create UI | HoangVu | Use "DIV tag" to created popup when move mouse "IMG tag" and Carousel. |  | 3 | 3 | 16/10/2020 | 16/10/2020 | 1 | 1
Create function logic
|  |  |  | Container Main Image / Makeup / Popup | Create UI | HoangVu | Use "DIV tag" to created popup when move mouse "IMG tag" and Carousel. |  | 3 | 3 | 16/10/2020 | 16/10/2020 | 1 | 1
Create function logic
|  |  |  | Container Main Image / Gift / Popup | Create UI | HoangVu | Use "DIV tag" to created popup when move mouse "IMG tag" and Carousel. |  | 3 | 3 | 17/10/2020 | 17/10/2020 | 1 | 1
Create function logic
|  |  |  | Container Main Image / Fashion / Popup | Create UI | HoangVu | Use "DIV tag" to created popup when move mouse "IMG tag" and Carousel. |  | 3 | 3 | 17/10/2020 | 17/10/2020 | 1 | 1
Create function logic
|  |  |  | Container Footer Top Content | Create UI | HoangVu | Use "DIV, P, INPUT tag" to create content. |  | 3 | 3 | 19/10/2020 | 19/10/2020 | 1 | 1
[5 empty] | Create function logic |  | Create function input email to recive from Bookbuy.vn
|  |  | FOOTER | Container Footer Middle Content | Create UI | HoangVu | Use "DIV, P, UL tag" to create content. |  | 3 | 3 | 19/10/2020 | 19/10/2020 | 1 | 1
Create function logic
|  |  |  | Container Footer Bottom Content | Create UI | HoangVu | Use "DIV, P, UL tag" to create content. |  | 3 | 3 | 20/10/2020 | 20/10/2020 | 1 | 1
Create function logic

## Helppage
STT | Features | Screen | Component | Sub Component | Task | Assignee | Detail | Pull Request (Link Github) | Estimated Hour (h) | Actual Hour (h) | Start Date | Finish Date | Sprint | Phase | Memo
1 | Home | Help page | Header | navigator top home page | Create UI | HoangVu | Use "UL tag" to create main navigator top. |  | 3 | 3 | 2020-11-01 | 2020-11-01 | 1 | 1
2 |  |  |  |  | Create function logic
|  |  |  | navigator top | Create UI | HoangVu | Use "UL tag" to create main navigator top. It have left menu + right menu. |  | 3 | 3 | 2020-11-02 | 2020-11-02 | 1 | 1
Create function logic
|  |  |  | navigator top/left | Create UI | HoangVu | Have 3 item inside left menu ( Tro Giup, Tin Tuc, Khuyen Mai), use image PNG to create icon menu left. |  | 2 | 1 | 2020-11-02 | 2020-11-02 | 1 | 1
Create function logic
|  |  |  | navigator top/right | Create UI | HoangVu | Have 3 item inside right menu ( Uu dai va tien ich, Kiem tra don hang, Dang nhap, Dang ky), use image PNG to create icon menu rigt. |  | 2 | 1 | 2020-11-03 | 2020-11-03 | 1 | 1
Create function logic
3 |  |  |  | Header middle/ Logo Page | Create UI | HoangVu | Use file PNG. Position: on the left page. Size: 117*35 px. |  | 1 | 1 | 2020-11-04 | 2020-11-04 | 1 | 1
4 |  |  |  |  | Create function logic
|  |  |  | Header middle/ Search bar | Create UI | HoangVu | Use "Input tag", it on the middle with icon search, position: middle |  | 1 | 0.5 | 2020-11-04 | 2020-11-04 | 1 | 1
[5 empty] | Create function logic | HoangVu | input data and press search icon to call searchItem(parameter) |  | 3 | 3 | 2020-11-04 | 2020-11-04 | 1 | 1
|  |  |  | Header middle/ Logo search | Create UI | HoangVu | Use file PNG, position: inside search bar |  | 1 | 1 | 2020-11-06 | 2020-11-06 | 1 | 1
|  |  |  | Header middle/ Logo Hotline | Create UI | HoangVu | Use file PNG, position: right middle header bar |  | 1 | 1 | 2020-11-06 | 2020-11-06 | 1 | 1
|  |  |  | Header middle/ Text Hotline | Create UI | HoangVu | Use "P tag" to create. Position: on the right Logo Hotline |  | 1 | 1 | 2020-11-06 | 2020-11-06 | 1 | 1
|  |  |  | Header middle/ Logo Cart | Create UI | HoangVu | Use file PNG, position: right middle header bar |  | 1 | 1 | 2020-11-06 | 2020-11-06 | 1 | 1
|  |  |  | Header middle/ Text Cart | Create UI | HoangVu | Use "P tag" to create. Position: on the right Logo Cart |  | 1 | 1 | 2020-11-06 | 2020-11-06 | 1 | 1
|  |  |  | Header bottom/ Icon Item List | Create UI | HoangVu | Use "a, img, span tag" to create. Position: on the left |  | 1 | 1 | 2020-11-07 | 2020-11-07 | 1 | 1
|  |  |  | Header bottom/ Text Item List | Create UI | HoangVu | Use "a, img, span tag" to create. Position: on the right Logo Item List |  | 1 | 1 | 2020-11-07 | 2020-11-07 | 1 | 1
5 |  |  |  | Header bootom/ menu right | Create UI | HoangVu | Use "a,img,span tag" to create. |  | 1 | 1 | 2020-11-07 | 2020-11-07 | 1 | 1
|  |  | Body | Main Menu | Create UI | HoangVu | Use "nav, ul tag" create main menu. |  | 3 | 3 | 2020-11-08 | 2020-11-08 | 1 | 1
[5 empty] | Create function logic | HoangVu
8 |  |  |  | Sub Menu | Create UI | HoangVu | Use "UL tag" to created. Use display: none. Hidden submenu. |  | 5 | 5 | 2020-11-09 | 2020-11-09 | 1 | 1
9 |  |  |  |  | Create function logic | HoangVu | Create link to another page. |  | 1 | 1 | 2020-11-09 | 2020-11-09
10 |  |  |  | Sidebar | Create UI | HoangVu | Use "UL tag" to created sidebar. And use reponsive to show sidebar . |  | 5 | 5 | 2020-11-10 | 2020-11-10 | 1 | 1
11 |  |  |  |  | Create function logic |  | Use Jquery Toogle() to hide and show. |  | 1 | 1 | 2020-11-12 | 2020-11-12 | 1 | 1
14 |  |  |  | Container Main Image | Create UI | HoangVu | Use "IMG tag" to created. |  | 2 | 2 | 2020-11-12 | 1112/2020 | 1 | 1
[5 empty] | Create function logic | [7 empty] | 1 | 1
|  |  |  | Container Main Content | Create UI | HoangVu | Use "DIV,P,SPAN, IMG, TABLE tag" to created. |  | 6 | 6 | 13/11/2020 | 14/11/2020 | 1 | 1
15 |  |  |  |  | Create function logic | HoangVu
|  |  | FOOTER | Container Footer Top Content | Create UI | HoangVu | Use "DIV, P, INPUT tag" to create content. |  | 3 | 3 | 14/11/2020 | 114/11/2020 | 1 | 1
[5 empty] | Create function logic |  | Create function input email to recive from Bookbuy.vn
|  |  |  | Container Footer Middle Content | Create UI | HoangVu | Use "DIV, P, UL tag" to create content. |  | 3 | 3 | 15/11/2020 | 15/11/2020 | 1 | 1
Create function logic
|  |  |  | Container Footer Bottom Content | Create UI | HoangVu | Use "DIV, P, UL tag" to create content. |  | 3 | 3 | 16/11/2020 | 16/11/2020 | 1 | 1
Create function logic

## Registerpage
STT | Features | Screen | Component | Sub Component | Task | Assignee | Detail | Pull Request (Link Github) | Estimated Hour (h) | Actual Hour (h) | Start Date | Finish Date | Sprint | Phase | Memo
1 | Home | Register Page | Header | navigator top home page | Create UI | HoangVu | Use "UL tag" to create main navigator top. |  | 0.5 | 0.5 | 17/11/2020 | 17/11/2020 | 1 | 1
2 |  |  |  |  | Create function logic
|  |  |  | navigator top | Create UI | HoangVu | Use "UL tag" to create main navigator top. It have left menu + right menu. |  | 1 | 1 | 17/11/2020 | 17/11/2020 | 1 | 1
Create function logic
3 |  |  |  | Header middle/ Logo Page | Create UI | HoangVu | Use file PNG. Position: on the left page. Size: 117*35 px. |  | 1 | 1 | 17/11/2020 | 17/11/2020 | 1 | 1
4 |  |  |  |  | Create function logic
|  |  | Body | Main Form | Create UI | HoangVu | Use "Form tag" to created. |  | 4 | 4 | 18/11/2020 | 18/11/2020 | 1 | 1
[5 empty] | Create function logic | HoangVu
|  |  |  | Main Form / Input element | Create UI | HoangVu | Use "Input, Select Option tag" to created. |  | 4 | 4 | 18/11/2020 | 18/11/2020 | 1 | 1
[5 empty] | Create function logic | HoangVu | Create function input Register User |  | 6 | 6 | 18/11/2020 | 18/11/2020
8 |  |  |  | Main Form / LogIn Tab | Create UI | HoangVu | Use "A, SPAN tag" to created. |  | 4 | 4 | 18/11/2020 | 18/11/2020 | 1 | 1
9 |  |  |  |  | Create function logic | HoangVu | Create link to Login Page |  | 1 | 1

## LogInpage
STT | Features | Screen | Component | Sub Component | Task | Assignee | Detail | Pull Request (Link Github) | Estimated Hour (h) | Actual Hour (h) | Start Date | Finish Date | Sprint | Phase | Memo
1 | Home | LogIn Page | Header | navigator top home page | Create UI | HoangVu | Use "UL tag" to create main navigator top. |  | 0.5 | 0.5 | 19/11/2020 | 19/11/2020 | 1 | 1
2 |  |  |  |  | Create function logic
|  |  |  | navigator top | Create UI | HoangVu | Use "UL tag" to create main navigator top. It have left menu + right menu. |  | 1 | 1 | 19/11/2020 | 19/11/2020 | 1 | 1
Create function logic
3 |  |  |  | Header middle/ Logo Page | Create UI | HoangVu | Use file PNG. Position: on the left page. Size: 117*35 px. |  | 1 | 1 | 19/11/2020 | 19/11/2020 | 1 | 1
4 |  |  |  |  | Create function logic
|  |  | Body | Main Form | Create UI | HoangVu | Use "Form tag" to created. |  | 2 | 2 | 20/11/2020 | 20/11/2020 | 1 | 1
[5 empty] | Create function logic | HoangVu
|  |  |  | Main Form / Input element | Create UI | HoangVu | Use "Input, Select Option tag" to created. |  | 2 | 2 | 20/11/2020 | 20/11/2020 | 1 | 1
[5 empty] | Create function logic | HoangVu | Create function Login |  | 3 | 3 | 20/11/2020 | 20/11/2020